## 2025~2026新人学习内容及时间安排
TBD
Done
On-going
Delay
Git 代码提交和管理贯穿所有项目, 所有工作成果都提交上代码仓库
阅读协议是了解清楚协议某个层次是处理什么样的逻辑，出现问题能清楚知道大概在哪一层有问题, 协议的阅读贯穿整个开发的流程, 当作字典来翻查 (不要企图第一次就完全读懂协议，遇到不懂记录下来，然后跳过)
2025~2026/时间轴 | Dec. /12 |  |  |  | Jan. /1 |  |  |  | Feb. /2 |  |  |  | Mar. /3 |  |  |  | Apr. /4 |  |  |  | May. /5
| W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
学习内容: | Dec. /12 W3: MCU / FreeRTOS; Jan. /1 W7: BLE; Feb. /2 W12: Zigbee; Mar. /3 W15: Zigbee; Apr. /4 W21: Thread; May. /5 W24: Matter
功能模块 | RT58x System, IC架构, 指标 | RT58x Peripheral (iic, spi, iis, uart, pwm) | Free RTOS | Free RTOS 整理Report(PPT)汇报学习成果 | GAP | GATT | SMP | HOGP 汇报成果 | HRS/BAS | APS | ZCL | ZCL (汇报成果) | 涂鸦Zigbee 模块案例 | NWK | ZDO | ZDO (汇报成果) | SMP | MAC | Thread | Thread (OTBR) | Thread (汇报成果) | Matter Cluster | Matter 灯/开关/插座/门磁 | Matter RCP (网关)
完成情况:
备注工作内容: | RT581，RT582，RT583， RT584H/L | 用RT58x系列，对接传感器， 调试代码做出效果 | 参考STM32的教材，一半看书，一半调代码 移植freeRTOS工程范例 |  | 阅读蓝牙Profile 协议 | Ellysis 抓包工具 使用 |  | 自己写一个HID蓝牙键盘/鼠标代码 (参考nordic范例) | 做一个心率，血糖蓝牙手环或者蓝牙透传 | 阅读Zigbee协议 （zBoss源码） |  |  | 做一个私有的zigbee cluster 实现zigbee网关与设备端的通讯 | zigbee 入网流程 |  |  | Zigbee 安全加密 | 802.15.4协议, Phy | Thread 协议阅读 | 熟悉API，SDK通讯范例 | Thread 多点组网 | 了解matter的编译流程，阅读Matter 协议 | ZAP 自动cluster配置工具
|  | 熟悉SDK 的API 用法以及参数条件 |  |  | 熟悉SDK 的相关的API 用法以及参数条件, 多熟悉BLE应用层代码 | [5 empty] | 熟悉SDK 的相关API 用法以及参数条件, 多熟悉Zigbee应用层代码 | [7 empty] | 熟悉SDK 的Thread 的 API 用法，参数条件 |  |  | Matter SDK 的开发
2026/时间轴 | Dec. /12 W3: Jun. / 6; Jan. /1 W7: Jul. /7; Feb. /2 W11: Aug.
| W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38
学习内容: | Jun. / 6 W27: Matter
功能模块 | Jun. / 6 W27: Matter RCP (网关); Jun. / 6 W28: Matter RCP (汇报成果)
完成情况: | bar: Jun. / 6 W27 to Jun. / 6 W28
备注工作内容:
Matter SDK 的开发
熟悉SDK 的相关的API 用法以及参数条件, 多熟悉BLE应用层代码
| Jul. /7 W31: Start; Jul. /7 W33: CNY(放假) |  |  |  | Sep. |  |  |  | Oct. |  |  |  | Nov.
[16 empty] | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50
TBD
[17 empty] | 十一假期 |  |  |  |  | 五一假期
Ble Mesh 相关
|  |  | Mesh Profile | Mesh Profile | Mesh Model | Mesh Model | Mesh Model | 整理Report(PPT)汇报成果

## 参考书目
模块优先级 | 参考书目: | 精读工作中会用到的章节(查漏补缺,熟悉的内容可跳过) | 备注 | 学习目标
2 | BLE/Mesh/HID/HOGP | Core_v5.3.pdf | 5.0+版本即可 | 1.掌握常用的BLE规范以及应用协议,包括蓝牙加密/广播流程/连线流程; 2. 应用层如 串口透传/HOGP/心率/血糖等BLE应用开发; 3. BLE Mesh 通信流程以及协议规范，常见应用代码开发;
|  | HID_v1.1.1.pdf | USB HID
|  | HIDS_SPEC_V10.pdf | 蓝牙HID
|  | HOGP_SPEC_V10.pdf | 蓝牙HOGP
hid1_11.pdf
hut1_21_0.pdf
|  | MshPRFv1.0.1.pdf | Mesh 基础Profile
|  | MshMDLv1.0.1.pdf | Mesh 通信模型
MeshDeviceProperties.pdf
3 | Zigbee | 802.15.4-2015.pdf | 802.15.4 物理层规范(了解) | 1. 掌握Zigbee协议栈的不同层的功能和作用，重点掌握配网流程，了解网络层路由寻址和消息转发的工作原理; 2. 掌握zigbee通信的常见cluster以及应用场景; 3. 基于RT58x 能独立完成Zigbee 应用层产品的开发;
|  | ZigBee2007协议规范.pdf | 中文版辅助入门
|  | docs-05-3474-21-0csg-zigbee-specification.pdf | Zigbee基础Spec
|  | 07-5123-06-zigbee-cluster-library-spec.pdf | ZCL
|  | 13-0402-13-00zi-Base-Device-Behavior-Specification-2-1.pdf | BDB
|  | docs-09-5499-26-batt-zigbee-green-power-specification.pdf | Green Power
|  | 涂鸦产品规范 | 常用/典型产品规范,如开关, 传感器
1 | MCU | ARM Cortex-M3与Cortex-M4权威指南.pdf | ARM MCU平台调试 | 1. 熟悉ARM 系列MCU的内部资源以及调试方法; 2. 结合RT58x MCU的外设驱动代码来熟悉MCU平台的相关资源; 3. 熟悉Free RTOS操作系统的常见API以及使用方法; 4. 基于RT58x 熟悉外设通信的常见协议;
|  | Mastering_the_FreeRTOS_Real_Time_Kernel-A_Hands-On_Tutorial_Guide.pdf | Free RTOS
FreeRTOS_Reference_Manual_V10.0.0.pdf
freertos-kernel-developer-guide-aws.pdf
正点原子STM32F4 版的FreeRTOS 文档;
|  | 熟悉I2C/SPI/PWM/UART/IR等协议波形以及分析方法 | 协议比较散, 请自行搜集资料
| Git 代码管理 | Git 权威指南
4 | Matter/Thread | Matter-1.2-Core-Specification.pdf | 最新Matter 协议已经到v1.5, 可以暂定用v1.2 进行基本的概念的理解和学习 Thread 参考v1.3
Matter-1.2-Application-Cluster-Specification.pdf
Matter-1.2-Device-Library-Specification.pdf
Guidance-document-to-Matter-1.2-in-Chinese.pdf （中文版）
Threadv1.3.0Specification_3989_2.pdf (Thread协议v1.3)

## HID以及HOGP阅读方法
####################################################################################################### This guildline describes the sequence to read different files. Date: 2021/06/15 Description: These reading materials for customer who did not know HID or BLE HOGP(keyboard/Mouse) concepts before. ####################################################################################################### Documents: (1)USB relevated documents(from USB Official Website) 001. hid1_11.pdf 002. hut1_21_0.pdf (2)BLE HOGP relevated documents(from SIG Official Website) 003. HID_v1.1.1.pdf 004. HIDS_SPEC_V10.pdf 005. HOGP_SPEC_V10.pdf ############################# Note ################################################################ 1) hid1_11.pdf, full name is Device Class Definition for Human Interface Devices (HID) v1.1; Read chapter 6 Descriptiors firstly and you should understand the numerical meaning of every byte in HID maps. For example, after reading chapter-6, you should have no difficult to understand Appendix E. Appendix E: Example USB Descriptors for HID Class Devices =>E.6 Report Descriptor (Keyboard) =>E.10 Report Descriptor (Mouse) Furthermore, to be more specific, you should understand why 0xC0 means "End Collection", why 0x09 and 0x02 means "Usage (Mouse)". You have the basic ability to understand how these numbers are mapped to the text meaning, and vise versa(design a number map by HID Descriptor Tool) Note: you can find HID Descriptor Tool from USB org official website. 2)hut1_21_0.pdf, full name is HID Usage Tables FOR Universal Serial Bus (USB) v1.21 Read: a)Keyboard/Keypad Page(0x07) * b)Consumer Page(0x0C), very important chapter for HID keyboard(which includes HID standard key value) 3)HID_v1.1.1.pdf This document give you the basic concept how bluetooth make use of HID concept for wireless USB communication; It mainly discusses BR/EDR HID and the communication principle of the bluetooth stack. The concepts it mentioned are also useful for understanding the ble HID(HIDS and HOGP). 4)HIDS_SPEC_V10.pdf It describes the Profile of HID Service(includes Primary Service, Gatt characteristic, Gatt descriptor); I suppose you have a good knowledge of BLE Gatt communication. If not, read bluetooth Core Spec GATT chapter firstly. 5)HOGP_SPEC_V10.pdf Last but not least –something that is equally important even if it's mentioned at the end. This document shows you how HID over Gatt Profile works. You should understand HOGP is not a specific service, but is a profile. This porfile includes the HID Service, Device Information Service(DIS),Battery Service(BAS). It mainly explains the concpets of HOGP(Host and Device) and the relationship between different services.